## Sheet1
ID | Asset | Risk Statement | Threat Source | Vulnerability | Likelihood | Impact | Risk Score | Current Controls | Recommended Action | Risk Owner | Status | Target Date
R1 | Customer Database | Weak passwords may allow attackers to access customer records | External attacker | No MFA + weak password policy | 3 | 3 | 9 | Passwords only | Implement MFA + enforce strong password policy | IT Lead | In Progress | 2025-01-30
R2 | Laptops | Lost or stolen laptop may cause data exposure | Employee | Devices not encrypted | 2 | 3 | 6 | Antivirus installed | Enforce full-disk encryption + enable laptop tracking | IT Admin | Not Started | 2025-02-10
R3 | Email Accounts | Phishing attack may lead to credential theft | Cybercriminals | No phishing training | 3 | 2 | 6 | Basic spam filter | Roll out phishing awareness training + enable DMARC | HR + IT | Not Started | 2025-02-20
R4 | Web Application | SQL injection could allow database access | External attacker | No regular code review or security testing | 2 | 3 | 6 | Firewall only | Implement secure code review + quarterly pentest | Dev Team | In Progress | 2025-03-01
R5 | Backup Server | Backups may be deleted or corrupted by ransomware | Malware | Backups stored on same network | 2 | 3 | 6 | Daily backups | Move backups offline or to cloud with immutability | DevOps | Not Started | 2025-02-05
R6 | WiFi Network | Unauthorized access via weak WiFi password | Insider/visitor | Shared password for all employees | 3 | 2 | 6 | WPA2 enabled | Create guest WiFi + strong unique employee WiFi creds | IT Admin | Completed | 2025-01-05
R7 | Admin Credentials | Compromised admin accounts may give full system access | Insider/external | Shared admin accounts | 2 | 3 | 6 | Admin password shared via WhatsApp | Create individual admin accounts + enable audit logs | IT Lead | In Progress | 2025-01-31
R8 | Cloud Storage | Public bucket may leak sensitive files | Misconfiguration | Permissions too open | 2 | 3 | 6 | Folder-level ACLs only | Review and restrict all cloud storage permissions | Cloud Admin | Not Started | 2025-02-12
R9 | HR Data | Unauthorized access to employee records | Insider threat | No access review performed | 2 | 2 | 4 | Password-protected folder | Perform quarterly access review + remove stale accounts | HR Manager | Not Started | 2025-03-15
R10 | Software & Servers | Unpatched vulnerabilities may be exploited | External attacker | No patching schedule | 2 | 3 | 6 | Occasional updates | Implement monthly patch cycle + automation | DevOps | In Progress | 2025-02-01